## Personal Info
First Name | Last Name | Middle Name | Email | Experience (Years) | Join Pool Date | English (TOEIC)
Registered Presentation
Topic | Plan Present Date | Present Status (Done or not)
Insert your picture here

## Java Core
ID | Activity | Method | Planned Duration (Hour) | Trainer | Start Date | End Date | Actual Duration (Hours) | Status (Done, Not Started, On-going) | Note | Slide | Material
I1 | Training Plan Introduction |  | 0.5 | Tin Bui | 2016-10-20 | 2016-10-20 |  | Done
P1 | Agile Scrum Process | Training | 1 | Tin Bui | [5 empty] | material\agile-scrum process
M1 | Maven Training | Training | 1 | Tin Bui |  |  |  |  | Provide sample project
M2 | Maven Practice | Practice | 4 |  |  |  |  | Ignored
O1 | OOP Training | Training | 2 | Tin Bui |  |  |  | Done |  | material\oop and java core\java basics and oop | SCJP Sun Certified Programmer for Java 6 Exam 310-065
O2 | OOP Self-study | Self-Study | 8 |  |  |  |  | Done |  |  | SCJP Sun Certified Programmer for Java 6 Exam 310-065
JC1 | Java Core (basic) Training - Session 1 | Training | 2 | [6 empty] | material\oop and java core\java basics and oop | Core Java Vol 1 Fundamentals 8th Edition chapters: 1,2,3,4,5,6 ‘SCJP Sun Certified Programmer for Java 6 Exam 310-065’
JC2 | Java Core (basic) Self-study | Self-Study | 16 |  |  |  |  | Done |  |  | Core Java Vol 1 Fundamentals 8th Edition chapters: 1,2,3,4,5,6 ‘SCJP Sun Certified Programmer for Java 6 Exam 310-065’
JC3 | Java Code Conventions | Self-Study | 4 |  |  |  | 4 | Done |  | material\oop and java core\java code convention
JC4 | JavaDoc | Self-Study | 4 |  |  |  |  | Done |  | material\oop and java core\java code convention
E1 | Exercise 1: Java OOP - Shape Area | Exercise | 8 |  |  |  | 20 | Done |  | exercises\Java OOP Exercise 1 - Shape Area.docx
JC6 | Unit Test, JUnit and Mockito | Self-Study | 8 |  |  |  |  | Done |  | material\oop and java core\unit-test, junit and mockito
E1.1 | Exercise 1+: Junit and Mockito - Shape Area (cont.) | Exercise | 8 |  |  |  |  | Done |  | exercises\Java OOP Exercise 1 - Shape Area.docx
JC7 | Java Collections | Self-Study and Present | 16 |  |  |  |  | Done |  | material\oop and java core\java collections and generics | Core Java Vol 1 Fundamentals 8th Edition chapters: 13
JC8 | Java Core (basic) Training - Session 2 - Java Generics, IO… | Training | 2 | Tin Bui | [6 empty] | Core Java Vol 1 Fundamentals 8th Edition chapters: 12
E2 | Exercise 2: Collection and Generic | Exercise | 16 |  |  |  |  | Ignored | Need to provide a skeleton of the app for trainee | exercises\Java OOP Exercise 2 - Collection and Generic.docx
D1 | Design Patterns - Training | Training | 2 | Tin Bui | [5 empty] | material\oo design\design patterns | Design Patterns - HeadFirst
D2 | OOD - Training | Training | 2 | Tin Bui |  |  |  | Ignored |  | material\oo design\design principles
D3 | Design Patterns Self-study | Self-Study, Exercise | 16 |  |  |  |  | Done |  |  | Design Patterns - HeadFirst
JC9 | Java IO and Multithreading | Self-Study | 16 |  |  |  |  | Done |  | material\oop and java core\java io and socket | Core Java Vol 1 Fundamentals 8th Edition chapters: 14
JC10 | Java Concurrency | Self-Study | 16 |  |  |  |  | Done |  | material\oop and java core\java multithreading and concurrency | + Core Java Vol 1 Fundamentals 8th Edition chapters: 14 + Concurrent Programming.chm
E3 | Exercise 3: Java Multithreading | Exercise | 16 |  |  |  |  | Done |  | exercises\Java OOP Exercise 3 - Multithread.docx
JC11 | Java Reflection | Self-Study | 8 |  |  |  |  | Done |  | material\oop and java core\java reflection | Core Java Vol 1 Fundamentals 8th Edition chapters: 12
D4 | Modeling - UML | Self-Study | 2 |  |  |  |  | Ignored |  | material\oo design\modeling - UML
F1 | Final Execise: Java Coding Problem Exercise | Exercise | 24 |  |  |  |  | Done |  | exercises\Java Coding Problem.docx
|  |  | 25.3125 | Days
Note on I2: Author: Done, Not Started, On-Going

## Java Technologies (hidden)
Day | Activity | Duration (Hour) | Trainer | Status | Material | Comments
Monday | EI 1: Java Coding Problem | 8 | Team
Tuesday | EI 1: Java Coding Problem (complete code ) | 7 | Team
| Java Technologies: Spring, Spring MVC, Spring Restful, Hibernate/JPA, GWT, AngularJS | 1 | Trieu Ngo
Wednesday | Training: AngularJS Basics and GWT Basics | 2 | Trieu Ngo
| Self Studying | 6 | Team
Thursday | Seminar 1: Core Spring Technologies | 2 | Trieu Ngo
| Seminar 2: Spring MVC and Restful | 2 | Trieu Ngo
| Seminar 3: Hibernate/JPA Technologies | 2 | Trieu Ngo
Friday | ER: Java Coding Problem (meeting review) | 4 | Team
| ER: Java Coding Problem (final submission) | 4 | Team

## Business Domain (hidden)
Day | Activity | Duration (Hour) | Trainer | Status | Material | Comments
Monday | Training: Market Basics - S1, 2 & 3 | 4 |  |  | Slides and Videos
| Self-Study: Andrew Murdoch's document | 4 |  |  | Docs and Videos
Tuesday | AM's Document Explaination | 4
| Self-Study: Richard Sherbinski's Videos (1,2&3) | 4
Wednesday | Self-Study: Security operations | 8
Thursday | Training: Finance Market Module 1 | 2
| Training: Finance Market Module 2 | 2
| Self-Study: Security operations | 4
Friday | Training: Finance Market Module 3 | 2
| Training: Finance Market Module 4 | 2
| Self-Study: Security operations | 4

## Project Overview (hidden)
Day | Activity | Duration (Hour) | Trainer | Status | Material | Comments
Monday | Capital Markets Overview | 2 | Khanh Le
| FO Development Environment Setup | 5 | Trieu Ngo
Tuesday | FrontOffice Overview | 1.5 | Trieu Ngo
| FO Architecture | 1.5 | Trieu Ngo
| Exercise: FO US 1 - Fix UI | 4 | Team
Wednesday | Margin and BIR Overview | 1.5 | Nhat Pham
| Exercise Review: FO US 1 - Fix UI | 1.5 | Trieu Ngo
| Exercise: FO US 2 - New Service | 4 | Team
Thursday | Share Overview | 1.5 | Khanh Le
| Exercise Review: FO US 2 - New Service | 1.5 | Trieu Ngo
| Exercise: FO US 3 - Winzard Flow | 4 | Team
Friday | Syn~ Overview | 1.5 | Khanh Le
| Exercise Review: FO US 3 - Winzard Flow | 5.5 | Team